## Procurement Plan
= extension available
Reference | Project / Programme Name | Description | Trade / Type of Work | Status | Ongoing / One Off Project | Length | Tender Route | Framework | Current no. of suppliers | Proposed no. of suppliers | [Estimated] Publication Date* | [Estimated] Contract Start Date | Estimated Maximum Contract / Framework Value (exc. VAT) | Notes
AP2420 | Structural Design Services Framework | Framework set up for the provision of surveys and consultancy on Structural Design (4 suppliers) | Consultancy Structural Design Architects | Opportunity Closed | Ongoing | Max. 4 years (2 + 1 + 1) | Find A Tender: Restricted | Yes | N/A | 4 | 2024-10-25 | 2025-11-01 | 1000000
AP2359 | Interiors Refurbishment Framework | Undertaking sift strip out works along with internal refurbishment including construction, flooring, ceiling finishes, furniture, fixtures and equipment. - 2 suppliers | Construction Mixed Building Works Building Alterations | Opportunity Closed | Ongoing | Max. 4 years (2 + 1 + 1) | Below Threshold: Restricted | Yes | 2 | 2 | 2024-10-25 | 2025-11-01 | 4000000
AP25008 | Temporary Staff Framework | Provision of staff members on a temporary basis. | Temporary Staff | Out To Tender Closing: 08/08/2025 at 14:00 | Ongoing | Max. 5 years (2 + 1 + 1 + 1) | Find A Tender: Open Tender | Yes | N/A | 1 | 2025-06-27 | 2025-10-01 | 4000000
TBC | Legionella Monitoring Contract | Provision of a water testing services on a scheduled and ad hoc basis, including cleaning on a scheduled basis. | Legionella Testing Legionella Cleaning Repairs, Servicing and Maintenance | Not started | Ongoing | Max. 7 years (3 + 2 + 2) | Above Threshold Procurement | No | 1 | 1 | 2025-07-01 | 2025-12-28 | £900,000 (TBC)
TBC | Security Services Contract | Security at vacant properties, Key holding , Static Guarding, Mobile Patrols | Security Services Key holding Static Guarding Mobile Patrols | Not started | Ongoing | Max. 5 years (2 + 2 + 1) | Above Threshold Procurement | No | 1 | 1 | 2025-07-01 | 2025-12-28 | £1,600,000 (TBC) | Current end date 31/12/24 but if all extensions enacted, current arrangement set to end December 2025.
AP2482 | Windows and External Doors Framework | Framework for the supply and fit of windows and external doors - 3 suppliers | Window and Doors | Not started | Ongoing | Max. 5 years (2 + 1 + 1 + 1) | Open Tender with PQQ | Yes | 3 | 3 | 2025-08-01 | 2026-01-28 | £3,000,000 (TBC)
AP2495 | Asbestos Removals Framework | Works inc. the removal and safe disposal of toxic or hazardous materials, conducting contaminated ground treatment and the assistance of undertaking environmental audits and intrusive investigations/surveys. | Asbestos Removal | Not started | Ongoing | Max. 4 years (2 + 1 + 1) | Open Tender | Yes | 3 | 3 | 2025-08-01 | 2026-01-28 | £2,000,000 (TBC)
AP2496 | Roofing Framework | Works covering roof structures, roof coverings, roof drainage, roof lights, skylights and openings and roof features inc. Balustrades, handrails to roof edges and service walkways within roof voids. | Roof Replacements Roof Maintenance Roof Repair Flat Roofing Rubber Roofing | In preparation | Ongoing | Max. 5 years (2 + 1 + 1 + 1) | Above Threshold Procurement | Yes | 2 | 2 | 2025-09-01 | 2026-04-29 | £8,000,000 (TBC)
TBC | Waste Collection Contract | Collection, disposal and recycling of waste (include hazardous waste) from sites managed by Arc Partnership | Skip Hire Waste Disposal Waste Collection | Not started | Ongoing | TBC | Direct Award via ESPO (if VFM achieved) | No | 1 | 1 | N/A | 2026-04-01 | TBC
TBC | Solid Fuel RSM Contract | Provision of a repairs, servicing and maintenance (RSM) contract covering all elements associated with solid fuel heating systems. | Solid Fuel Appliances Repairs, Servicing and Maintenance | Not started | Ongoing | TBC | TBC | No | 1 | 1 | 2025-10-01 | 2026-04-01 | TBC
TBC | Electrical RSM Contract | Repairs, servicing and maintenance for electrical systems including 24/7 emergency breakdown. | Electrical Repairs, Servicing and Maintenance | Not started | Ongoing | TBC | Open Tender | No | 1 | 1 | 2025-10-01 | 2026-04-01 | TBC
TBC | Air Handling Plant and Air Conditioning RSM Contract | Repairs, servicing and maintenance for air handling plant and air conditioning including 24/7 emergency breakdown. | Air Conditioning Ventilation Repairs, Servicing and Maintenance | Not started | Ongoing | TBC | TBC | No | 1 | 1 | 2025-11-01 | 2026-07-01 | TBC
TBC | Temporary Site Accommodation Contract | Provision of temporary site accommodation and equipment. | Temporary Site Cabins | Not started | Ongoing | TBC | TBC | No | 1 | 1 | 2025-11-01 | 2026-07-01 | TBC
TBC | General Building RSM Contract | General building repairs service covering multiple trades, temporary works and an out of hours service. | General Repairs and Maintenance Mixed Building Works | Not started | Ongoing | TBC | TBC | No | 1 | 1 | 2026-01-01 | 2026-08-01 | TBC
TBC | Groundwork RSM Contract | General groundwork repairs service covering multiple trades. | External Repairs Drainage Fencing and Gates Site Clearances Repairs, Servicing and Maintenance | Not started | Ongoing | TBC | TBC | No | 1 | 1 | 2026-01-01 | 2026-08-01 | TBC
TBC | Joinery RSM Contract | General joinery repairs service covering minor painting & decorating, glazing and suspended ceilings, including an out of hours service. | Joinery Carpentry Repairs, Servicing and Maintenance | Not started | Ongoing | TBC | TBC | No | 1 | 1 | 2026-01-01 | 2026-08-01 | TBC
TBC | Roofing RSM Contract | Roofing repairs including guttering works both in and an out of hours service. | Roof Maintenance Roof Repair Flat Roofing Rubber Roofing Repairs, Servicing and Maintenance | Not started | Ongoing | TBC | TBC | No | 1 | 1 | 2026-01-01 | 2026-08-01 | TBC
TBC | Lightning Protection and Fall Arrest Equipment RSM Contract | Provision of a repairs, servicing and maintenance (RSM) contract covering all elements associated with lightning protection and fall arrest equipment. | Lightning Protection Fall Protection Equipment Repairs, Servicing and Maintenance | Not started | Ongoing | TBC | TBC | No | 1 | 1 | 2026-01-01 | 2026-09-01 | TBC
TBC | Mechanical RSM Contract | Mechanical and plumbing repair and maintenance works both in and an out of hours and servicing. | Mechanical Plumbing Repairs, Servicing and Maintenance | Not started | Ongoing | TBC | Open Tender | No | 1 | 1 | 2026-01-01 | 2026-08-01 | £3,000,000 (TBC)
TBC | Mechanical and Electrical Engineering Framework | A 4 lot framework (2 providers each discipline) for Mechanical and Electrical Engineering works for Construction Services in Nottinghamshire | Mechanical Plumbing Electrical | Not started | Ongoing | TBC | Above Threshold Procurement | Yes | 3 | 2 - Mechanical 2 - Electrical | 2026-02-01 | 2026-11-01 | TBC
TBC | Maintenance of Portable Firefighting Equipment Contract | Servicing and replacement of fire extinguishers and fire blankets | Fire Fighting Equipment Fire Extinguishers | Not started | Ongoing | TBC (Long Term) | Open tender | No | 1 | 1 | 2026-04-01 | 2026-10-01 | TBC | Current end date 30/09/24 but if all extensions enacted, current arrangement set to end September 2026.
TBC | Lifts and Hoists Servicing and Maintenance | Lift & Hoists Servicing & Maintenance, Passenger and goods lifts at various locations in Nottinghamshire. | Lift Maintenance Lifting Equipment Maintenance | Not started | Ongoing | TBC | Open | No | 1 | 1 | 2026-04-01 | 2027-01-01 | TBC
TBC | Temporary Heating & Hot Water Framework | Provision of temporary heating and hot water equipment to sites and buildings as required. | Mechanical Temporary Equipment Equipment Hire | Not started | Ongoing | TBC | TBC | TBC | 1 - Temp Hot Water 1 - Temp Portable Heating | 1 | 2026-04-01 | 2026-10-01 | 640000
AP2411 | M&E Design Services Framework | Framework set up for the provision of surveys and consultancy on Mechanical & Electrical Design (4 suppliers) | Consultancy Mechanical Design Architects | Opportunity Closed | Ongoing | Max. 4 years (2 + 1 + 1) | Find A Tender: Restricted | Yes | N/A | 4 | 2026-09-30 | 2027-04-28 | 800000
TBC | Construction Framework | Framework for general construction works | Mixed Building Works Repairs, Servicing and Maintenance (minor element) | Not started | Ongoing | TBC | Above Threshold Procurement | Yes | 3 | TBC | 2026-10-01 | 2027-06-01 | 4000000
TBC | External Works Framework | Framework for general external works | Tarmac Ground Works Drainage Fencing and Gates Site Clearances Repairs, Servicing and Maintenance (minor element) | Not started | Ongoing | TBC | Above Threshold Procurement | Yes | 5 | TBC | 2026-10-01 | 2027-06-01 | 4000000
TBC | Intruder Alarm RSM Contract | Repairs, servicing and maintenance of intruder alarms including 24/7 emergency breakdown and provision of a monitoring service for intruder and fire alarms. | Intruder Alarms Monitoring Intruder and Fire Alarms Repairs, Servicing and Maintenance | Not started | Ongoing | TBC | TBC | No | 1 | 1 | 2026-11-01 | 2027-04-01 | TBC
TBC | Asbestos Analyst Consultancy | Sampling and analysis of asbestos related or suspected materials inc. air monitoring | Asbestos Consultancy | Not started | Ongoing | TBC | TBC | Yes | 3 | 3 | 2026-11-01 | 2027-04-01 | 800000
TBC | Fire Alarm RSM Contract | Repairs, servicing and maintenance for fire alarm and firefighting systems including 24/7 emergency breakdown. | Fire Alarms Repairs, Servicing and Maintenance | Not started | Ongoing | TBC | TBC | No | 1 | 1 | 2026-12-01 | 2027-05-01 | TBC
TBC | Security Systems RSM Contract | Repairs, servicing and maintenance for security systems (CCTV, Access Control) including 24/7 emergency breakdown. | CCTV Systems Security Doors Security Door Systems Repairs, Servicing and Maintenance | Not started | Ongoing | TBC | TBC | No | 1 | 1 | 2027-01-01 | 2027-06-01 | TBC
TBC | Contract Management and Reporting Software | SaaS software to help facilitate the management of NEC contracts | Computer Software | Not started | Ongoing | TBC | Direct Award via Crown Commercial Services G-Cloud (if VFM achieved) | No | 1 | 1 | N/A | 2027-11-26 | TBC | Existing arrangement ends 27/11/2027 but will seek to undertake a direct call-off from CCS G-Cloud for this requirement
Note on H2: Identified routes based on Procurement Act 2023
Note on L2: Quarters (Q) are recorded from April to March
Note on M11: (if extension not taken)
Note on L12: (if extension not taken)
Note on M12: (if extension not taken)
Note on L13: (if extension not taken)
Note on M13: (if extension not taken)
Note on L14: (if extension not taken)
Note on M14: (if extension not taken)
Note on L15: (if extension not taken)
Note on M15: (if extension not taken)
Note on L16: (if extension not taken)
Note on M16: (if extension not taken)
Note on L17: (if extension not taken)
Note on M17: (if extension not taken)
Note on L18: (if extension not taken)
Note on M18: (if extension not taken)
Note on L19: (if extension not taken)
Note on M19: (if extension not taken)
Note on L20: (if extension not taken)
Note on M20: (if extension not taken)
Note on L21: (if extension not taken)
Note on M21: (if extension not taken)
Note on L24: (if extension not taken)
Note on M24: (if extension not taken)
Note on L25: (if extension not taken)
Note on M25: (if extension not taken)
Note on L26: (if extension not taken)
Note on M26: (if extension not taken)
Note on L27: (if extension not taken)
Note on M27: (if extension not taken)
Note on L28: (if extension not taken)
Note on M28: (if extension not taken)
Note on L29: (if extension not taken)
Note on M29: (if extension not taken)
Note on L30: (if extension not taken)
Note on M30: (if extension not taken)
Note on L31: (if extension not taken)
Note on M31: (if extension not taken)
Note on L32: (if extension not taken)
Note on M32: (if extension not taken)

## Procurement Pipeline
Procurement Pipeline
Procurement Planning Stage
Market Engagement
Procurement Stage
Mobilisation
Procurements in progress
|  | Start Date | [7 empty] | 2025 | [11 empty] | 2026 | [11 empty] | 2027 | [11 empty] | 2028 | [11 empty] | 2029 | [11 empty] | 2030 | [11 empty] | 2031 | [11 empty] | 2032
Ref | Name | PP- Procurement Plan |  | ME- Market Engagement |  | P- Procure |  | M- Mobilisation | time axis 2025-01-01 to 2033-01-01
AP2420 | Structural Design Services Framework | 2024-08-23 | 2024-09-23 | 2024-09-24 | 2024-10-24 | 2024-10-25 | 2025-10-31 | 2025-11-01 | 2025-11-21 | bar: 2025-01-01 to 2025-11-01
AP2359 | Interiors Refurbishment Framework | 2024-08-23 | 2024-09-23 | 2024-09-24 | 2024-10-24 | 2024-10-25 | 2025-05-31 | 2025-06-01 | 2025-11-01 | bar: 2025-01-01 to 2025-11-01
TBC | Temporary Staff Framework | 2025-02-01 | 2025-03-31 | 2025-04-01 | 2025-04-30 | 2025-05-01 | 2025-09-03 | 2025-09-04 | 2025-10-01 |  | pp | pp | me | p | p | p | p | p | m
TBC | Legionella Monitoring Contract | 2025-05-03 | 2025-06-30 |  |  | 2025-07-01 | 2025-11-30 | 2025-12-01 | 2025-12-28 | [10 empty] | p | m | bar: p to m
TBC | Security Services Contract | 2025-05-03 | 2025-06-30 |  |  | 2025-07-01 | 2025-11-30 | 2025-12-01 | 2025-12-28 | [10 empty] | p | m | bar: p to m
AP2482 | Windows and External Doors Framework | 2025-05-03 | 2025-06-30 | 2025-07-01 | 2025-07-31 | 2025-08-01 | 2025-12-31 | 2026-01-01 | 2026-01-28 | [5 empty] | pp | me | p | p | p | p | p | m
AP2495 | Asbestos Removals Framework | 2025-05-03 | 2025-06-30 | 2025-07-01 | 2025-07-31 | 2025-08-01 | 2025-12-31 | 2026-01-01 | 2026-01-28 | [5 empty] | pp | me | p | p | p | p | p | m
AP2496 | Roofing Framework | 2025-06-03 | 2025-07-31 | 2025-08-01 | 2025-08-31 | 2025-09-01 | 2026-03-31 | 2026-04-01 | 2026-04-29 | [6 empty] | pp | me | p | p | p | p | p | p | p | m
TBC | Waste Collection Contract | 2026-01-01 | 2026-01-31 |  |  | 2026-02-01 | 2026-03-04 | 2026-03-05 | 2026-04-01 | [12 empty] | pp | p | p | m
TBC | Solid Fuel RSM Contract | 2025-07-04 | 2025-08-31 | 2025-09-01 | 2025-09-30 | 2025-10-01 | 2026-03-04 | 2026-03-05 | 2026-04-01 | [7 empty] | pp | me | p | p | p | p | p | p | m
TBC | Electrical RSM Contract | 2025-07-04 | 2025-08-31 | 2025-09-01 | 2025-09-30 | 2025-10-01 | 2026-03-04 | 2026-03-05 | 2026-04-01 | [7 empty] | pp | me | p | p | p | p | p | p | m
TBC | Air Handling Plant and Air Conditioning RSM Contract | 2025-08-04 | 2025-10-01 | 2025-10-02 | 2025-10-31 | 2025-11-01 | 2026-06-03 | 2026-06-04 | 2026-07-01 | [16 empty] | p | p | m | bar: me me to m m
TBC | Temporary Site Accommodation Contract | 2025-08-04 | 2025-10-01 | 2025-10-02 | 2025-10-31 | 2025-11-01 | 2026-06-03 | 2026-06-04 | 2026-07-01 | [16 empty] | p | p | m | bar: me me to m m
TBC | Auto Doors RSM | 2025-10-04 | 2025-12-01 | 2025-12-02 | 2025-12-31 | 2026-01-01 | 2026-06-03 | 2026-06-04 | 2026-07-01 | [16 empty] | p | p | m | bar: p p to m m
TBC | General Building RSM Contract | 2025-10-04 | 2025-12-01 | 2025-12-02 | 2025-12-31 | 2026-01-01 | 2026-07-04 | 2026-07-05 | 2026-08-01 | [16 empty] | p | p | p | m | bar: p p to m m
TBC | Mechanical RSM Contract | 2025-10-04 | 2025-12-01 | 2025-12-02 | 2025-12-31 | 2026-01-01 | 2026-07-04 | 2026-07-05 | 2026-08-01 | [16 empty] | p | p | p | m | bar: p p to m m
TBC | Groundwork RSM Contract | 2025-10-04 | 2025-12-01 | 2025-12-02 | 2025-12-31 | 2026-01-01 | 2026-07-04 | 2026-07-05 | 2026-08-01 | [16 empty] | p | p | p | m | bar: p p to m m
TBC | Joinery RSM Contract | 2025-10-04 | 2025-12-01 | 2025-12-02 | 2025-12-31 | 2026-01-01 | 2026-07-04 | 2026-07-05 | 2026-08-01 | [16 empty] | p | p | p | m | bar: p p to m m
TBC | Roofing RSM Contract | 2025-10-04 | 2025-12-01 | 2025-12-02 | 2025-12-31 | 2026-01-01 | 2026-07-04 | 2026-07-05 | 2026-08-01 | [16 empty] | p | p | p | m | bar: p p to m m
TBC | Lightning Protection and Fall Arrest Equipment RSM Contract | 2025-10-04 | 2025-12-01 | 2025-12-02 | 2025-12-31 | 2026-01-01 | 2026-08-04 | 2026-08-05 | 2026-09-01 | [16 empty] | p | p | p | p | m | bar: p p to m m
TBC | Mechanical and Electrical Engineering Framework | 2025-11-04 | 2026-01-01 | 2026-01-02 | 2026-01-31 | 2026-02-01 | 2026-10-04 | 2026-10-05 | 2026-11-01 | [16 empty] | p | p | p | p | p | p | m | bar: p p to m m
TBC | Maintenance of Portable Firefighting Equipment Contract | 2026-01-02 | 2026-03-01 | 2026-03-02 | 2026-03-31 | 2026-04-01 | 2026-09-03 | 2026-09-04 | 2026-10-01 | [16 empty] | p | p | p | p | p | m | bar: p p to m m
TBC | Lifts and Hoists Servicing and Maintenance | 2026-01-02 | 2026-03-01 | 2026-03-02 | 2026-03-31 | 2026-04-01 | 2026-12-04 | 2026-12-05 | 2027-01-01 | [16 empty] | p | p | p | p | p | p | p | p | m | bar: p p to m m
TBC | Temporary Heating & Hot Water Framework | 2026-01-02 | 2026-03-01 | 2026-03-02 | 2026-03-31 | 2026-04-01 | 2026-09-03 | 2026-09-04 | 2026-10-01 | [16 empty] | p | p | p | p | p | m | bar: p p to m m
TBC | Construction Framework | 2026-07-04 | 2026-08-31 | 2026-09-01 | 2026-09-30 | 2026-10-01 | 2027-05-04 | 2027-05-05 | 2027-06-01 | [19 empty] | pp | me | p | p | p | p | p | p | p | p | m
TBC | External Works Framework | 2026-07-04 | 2026-08-31 | 2026-09-01 | 2026-09-30 | 2026-10-01 | 2027-05-04 | 2027-05-05 | 2027-06-01 | [19 empty] | pp | me | p | p | p | p | p | p | p | p | m
TBC | Intruder Alarm RSM Contract | 2026-08-04 | 2026-10-01 | 2026-10-02 | 2026-10-31 | 2026-11-01 | 2027-03-04 | 2027-03-05 | 2027-04-01 | [20 empty] | pp | pp | p | p | p | p | p | m
TBC | Asbestos Analyst Consultancy | 2026-08-04 | 2026-10-01 | 2026-10-02 | 2026-10-31 | 2026-11-01 | 2027-03-04 | 2027-03-05 | 2027-04-01 | [20 empty] | pp | pp | p | p | p | p | p | m
TBC | Fire Alarm RSM Contract | 2026-09-03 | 2026-10-31 | 2026-11-01 | 2026-11-30 | 2026-12-01 | 2027-04-03 | 2027-04-04 | 2027-05-01 | [21 empty] | pp | me | p | p | p | p | p | m
TBC | Security Systems RSM Contract | 2026-10-04 | 2026-12-01 | 2026-12-02 | 2026-12-31 | 2027-01-01 | 2027-05-04 | 2027-05-05 | 2027-06-01 | [22 empty] | pp | pp | p | p | p | p | p | m
TBC | Contract Management and Reporting Software | 2027-01-01: N/A; 2027-05-04: 2027-10-29; 2027-05-05: 2027-10-30; 2027-06-01: 2027-11-26 | [34 empty] | m